RESEARCH PROPOSAL  ·  VERSION 2.0

When and Why Do RL Algorithms Differ in Autonomous Cyber Defense?

A Condition-Dependent Empirical Analysis of PPO, AWR, and AWAC

on the CybORG MiniCAGE Benchmark under Varying Attacker Strategies and Data Quality

| Project Type | Empirical Comparative Study — Condition-Dependent RL Analysis |
| --- | --- |
| Target Venue | IEEE Access / MDPI Electronics / Applied Sciences (Q3/Q4) |
| Timeline | 6 months (Weeks 1–24) |
| Environment | CybORG++ MiniCAGE (CAGE Challenge 2) |
| Design | 2 × 3 Factorial: Attacker Type × RL Algorithm (+2 ablations) |
| Hardware | Apple Silicon M4 (MPS), Python 3.11, Stable-Baselines3 |
| Team Size | 4 members |
| Version | v2.0 — Revised from comparison study to condition-dependent analysis |

# 1. Why This Proposal Was Revised

Version 1.0 of this proposal framed the study as a performance comparison of three RL algorithms on CybORG. While methodologically sound, that framing carries a fundamental weakness: a reviewer can always ask “So what?” A comparison table, however rigorous, does not constitute a scientific contribution unless it answers a generalizable question about the world.

The Core Upgrade: Compare → Explain

❌ v1.0 (Weak): "We compare PPO, AWR, and AWAC on CybORG." Reviewer response: "OK… so what? When should I use which?" ✅ v2.0 (Strong): "Under what conditions does offline pre-training accelerate convergence in autonomous cyber defense — and when does it fail?" Reviewer response: "This answers a real practitioner question. Let’s see the data."

# 2. Executive Summary

Reinforcement Learning offers a principled framework for training autonomous agents capable of detecting and responding to network intrusions in real time. However, the central unsolved practitioner question is not “which algorithm achieves the highest reward?” but rather: “Which algorithm should I deploy, given my specific operational constraints?”

This study provides the first condition-dependent empirical analysis of PPO (on-policy), AWR (offline), and AWAC (offline-to-online) in the CybORG MiniCAGE environment. By systematically varying two independently controlled factors — attacker strategy and offline data quality — we produce actionable insights about when each algorithmic paradigm excels and when it degrades. Crucially, we complement quantitative metrics with behavioral analysis, revealing qualitative differences in defensive strategy rather than merely reporting reward curves.

# 3. Research Questions

Core Research Question (RQ0)

Under what conditions does offline pre-training (AWR) or offline-to-online bridging (AWAC) outperform a well-tuned on-policy baseline (PPO) in autonomous cyber defense, as measured by sample efficiency, convergence stability, and behavioral robustness?

## 3.1 Sub-Questions

| ID | Factor | Question | Hypothesis |
| --- | --- | --- | --- |
| RQ1 | Attacker Strategy | Does algorithm ranking change between deterministic (B_line) and stochastic (RedMeander) attackers? | AWAC is more robust to stochastic attackers due to its off-policy critic; PPO is sufficient for deterministic attackers. |
| RQ2 | Data Quality | How sensitive are AWR and AWAC to the quality of the offline buffer (high-quality heuristic vs. low-quality random)? | AWR degrades sharply with low-quality data; AWAC’s online phase compensates partially. |
| RQ3 | Sample Efficiency | Which algorithm reaches 80% of maximum reward fastest, and does this ranking depend on attacker type? | Offline methods are more sample-efficient early but may plateau; AWAC sustains improvement longer. |
| RQ4 | Behavioral Strategy | Do the algorithms adopt qualitatively different defensive strategies, or do they converge to similar action patterns? | PPO explores more; AWAC exploits offline knowledge early, leading to different action distributions. |

These four sub-questions transform the study from a description ("AWAC scores X") into an explanation ("AWAC scores X because it handles stochastic attackers better when given high-quality offline data"). The latter is what earns reviewer respect.

# 4. Problem Statement & Research Gap

## 4.1 The Practitioner's Dilemma

A security engineer deploying an autonomous defense agent faces two hard constraints. First, online RL is unsafe: every training step is a live action on a production network. A naive PPO agent exploring its action space will inevitably execute destructive operations (e.g., removing legitimate users, blocking critical services). Second, offline RL is conservative: an AWR agent trained only on historical logs is blind to novel attack patterns not present in its buffer. The practitioner needs to know when the offline data is “good enough” to skip online training, and what “good enough” means in operational terms.

## 4.2 The Gap in Existing Literature

Existing CybORG research presents three key limitations that this study directly addresses:

| Limitation in Literature | What Is Missing | How We Address It |
| --- | --- | --- |
| PPO is the near-universal baseline; other paradigms rarely compared | No systematic comparison of on-policy vs offline vs offline-to-online in cyber | Three-algorithm, multi-condition factorial study |
| Results reported under a single attacker strategy | Algorithm rankings may reverse under different attacker behaviors | Controlled variation: B_lineAgent vs RedMeanderAgent |
| Offline buffer quality treated as a constant | Sensitivity to data quality is unknown; practitioners cannot know what buffer size/quality they need | High-quality vs low-quality buffer ablation |
| Evaluation limited to reward curves | No insight into why algorithms behave differently | Action distribution analysis, heatmaps, failure mode characterization |

# 5. Methodology

## 5.1 Experimental Design: 2 × 3 Factorial

The core experimental design is a 2 × 3 factorial crossing attacker type (2 levels) with RL algorithm (3 levels). Both factors are already available in CybORG without environment modification, making this design fully feasible within the project timeline. An additional buffer-quality ablation is run for AWR and AWAC only.

|  | B_lineAgent (Deterministic) | RedMeanderAgent (Stochastic) |
| --- | --- | --- |
| PPO (On-policy) | Cell 1 — Baseline A | Cell 2 — Baseline B |
| AWR (Offline, HQ Buffer) | Cell 3 — Offline A | Cell 4 — Offline B |
| AWAC (Offline→Online) | Cell 5 — Bridge A | Cell 6 — Bridge B |

Each of the 6 cells runs with 5 random seeds × 500K steps. The buffer-quality ablation adds 2 × 2 additional runs (AWR+AWAC under low-quality buffer, both attacker types). Total: 34 experimental runs, each approximately 5–7 hours on M4 MPS → feasible within 2 weeks of parallel compute.

## 5.2 Environment

All experiments use CybORG++ with the MiniCAGE wrapper (CAGE Challenge 2). MiniCAGE models a 3-subnet enterprise network; the Blue agent observes partial network state and selects from Monitor, Analyse, Remove, Restore, and Decoy actions. No environment modification is required: both attacker agents (B_line, RedMeander) ship with the CybORG++ distribution.

| Parameter | Value | Rationale |
| --- | --- | --- |
| Environment | CybORG++ MiniCAGE | Community standard, no custom code needed |
| Attacker agents | B_lineAgent, RedMeanderAgent | Deterministic vs. stochastic — built-in variation |
| Episode length | 100 steps | Standard CAGE-2 configuration |
| Eval episodes | 100 per checkpoint | Statistically reliable reward estimate |
| Seeds per cell | 5 | Enables variance estimation & significance testing |
| Training budget | 500K environment steps | Convergence observed in prior work by ~300K steps |
| HQ buffer source | Heuristic Blue agent (rule-based) | Provides good-quality transitions without exploration |
| LQ buffer source | Random Blue agent | Simulates poor historical data scenario |
| Buffer size | 50K transitions | ~10% of training budget — realistic offline scenario |

## 5.3 Algorithms

### PPO — On-Policy Baseline

- Standard Proximal Policy Optimization with Generalized Advantage Estimation (GAE, λ=0.95).

- Actor-Critic: 2 hidden layers, 256 neurons, ReLU activations.

- Trained entirely from online interaction with CybORG — no offline data.

### AWR — Offline Baseline

- Trains exclusively on a fixed replay buffer (no online interaction after buffer collection).

- Policy update: exponentially-weighted behavioral cloning using advantage weights exp(β·A).

- Run under both HQ (heuristic) and LQ (random) buffer to answer RQ2.

### AWAC — Offline-to-Online Bridge

- Phase 1 (offline): pre-trains on same HQ/LQ buffer as AWR using constrained policy updates.

- Phase 2 (online): fine-tunes with off-policy actor-critic using a replay buffer that grows with online experience.

- Implicit constraint prevents distribution shift during the offline-to-online transition.

### Ablations

- AWR-LQ: AWR trained on random-agent buffer — isolates data quality effect from algorithm choice.

- AWAC-LQ: AWAC pre-trained on random-agent buffer — tests whether online phase compensates for poor offline data.

- PPO-WarmStart: PPO initialized from AWR weights — separates warm initialization from AWAC’s off-policy critic.

## 5.4 Evaluation Metrics

Evaluation is three-dimensional: quantitative performance, training dynamics, and behavioral characterization. This is the critical upgrade over v1.0, which only planned reward curves.

| Dimension | Metric | Definition | Answers |
| --- | --- | --- | --- |
| Performance | Final reward (mean±std) | Mean episode reward over last 50 eval episodes across 5 seeds | Which algorithm performs best? |
| Performance | Success rate | % episodes where Blue prevents all host compromise | Operational relevance metric |
| Efficiency | Steps to 80% max reward | First step where smoothed reward ≥ 0.8× max | RQ3: Sample efficiency |
| Stability | Convergence variance | Std of reward across 5 seeds at 500K steps | Deployment reliability |
| Stability | Catastrophic action rate | % of actions causing network disruption (Remove on clean host) | Safety proxy for real deployment |
| Behavioral | Action distribution | Frequency histogram of each action type per algorithm | RQ4: Strategy differences |
| Behavioral | Compromise heatmap | Mean % time each host is compromised per algorithm | Which hosts does each agent protect best? |
| Behavioral | Failure episode analysis | Qualitative review of 10 worst episodes per algorithm | Why does each algorithm fail? |

## 5.5 Behavioral Analysis Protocol (The Key Differentiator)

Most RL papers stop at reward curves. This study adds a behavioral layer that transforms numbers into insight. The following analyses require only standard logging — no additional code beyond recording action choices and host states at each step.

- Action distribution plots: For each of the 6 main cells, plot the frequency of each Blue action (Monitor, Analyse, Remove, Restore, Decoy). PPO is expected to show more exploration (higher Monitor/Analyse); AWAC is expected to exploit offline knowledge early (higher Restore/Decoy).

- Host compromise heatmaps: Visualize which hosts are most frequently compromised under each algorithm. Reveals whether algorithms protect the network uniformly or prioritize certain subnets.

- Convergence trajectory comparison: Overlay learning curves for all 6 cells on the same axes, showing not just final performance but the shape of learning (monotonic vs. volatile vs. plateaued).

- Failure mode tagging: Manually review the 10 lowest-reward episodes per algorithm per attacker. Tag failure causes (e.g., “agent delayed Restore”, “agent over-used Remove”). This produces qualitative insight no metric can capture.

Why Behavioral Analysis Makes This Paper Publishable

Reviewers at Q3 journals see dozens of RL comparison papers per month. What makes them recommend “accept” is not a better number — it’s an answer to a question they couldn’t answer before reading the paper. The behavioral analysis section directly answers RQ4: “PPO agents monitor more; AWAC agents restore faster. This suggests that offline pre-training instills an exploitative bias that persists through online fine-tuning, which may be advantageous against fast-moving attackers but brittle against novel attack patterns not present in the offline buffer.” This is a finding. Numbers alone are not.

## 5.6 Hyperparameter Protocol

To ensure fair comparison, all algorithms share identical network architecture (2 hidden layers, 256 neurons, ReLU) and optimizer (Adam, lr=3×10⁻⁴). Algorithm-specific hyperparameters are tuned in a short grid search (10 seeds, 50K steps) before main experiments. All hyperparameter ranges and final configurations are reported in full in an appendix, ensuring reproducibility.

# 6. Contributions

## 6.1 Scientific Contributions

- First condition-dependent empirical analysis of PPO, AWR, and AWAC on CybORG MiniCAGE under controlled variation of attacker strategy and offline data quality.

- Empirical answer to when offline pre-training helps and when it fails — a practitioner-relevant question with no prior systematic answer in the ACD literature.

- Quantitative characterization of data quality sensitivity for offline RL in cyber defense — enabling practitioners to assess whether their historical logs are sufficient before committing to offline training.

- Behavioral fingerprinting of each algorithmic paradigm — revealing action-level differences in defensive strategy beyond reward metrics.

- Practical decision framework: a structured set of conditions (attacker type, data quality, compute budget) guiding algorithm selection for real ACD deployments.

## 6.2 Community Contributions

- Fully reproducible codebase: all 5 algorithms, hyperparameter configs, logging scripts, and evaluation pipelines released on GitHub under MIT license.

- Reproducibility report: step-by-step instructions for replication on Apple Silicon M-series and equivalent hardware — enabling resource-limited researchers to build on this work.

- Codebase serves as a foundation for subsequent studies (Priority-AWR, curriculum learning) without reimplementation.

# 7. Team Structure & Responsibilities

| Member | Role | Primary Responsibilities | Key Deliverable |
| --- | --- | --- | --- |
| M1 (Lead) | Project Lead & RL Eng. | Experimental design, PPO + AWAC implementation, factorial run orchestration, paper Sections 1–5 draft | Models PPO, AWAC + main draft |
| M2 | Algorithm Specialist | AWR implementation (HQ+LQ), buffer collection pipeline, hyperparameter search, ablation runs | Models AWR, AWR-LQ, AWAC-LQ |
| M3 | Env. & Infra. Eng. | CybORG++ setup, logging system design, action distribution + heatmap visualization, W&B dashboard | Infra + all figures |
| M4 | Analysis & Writing | Statistical analysis (CI, significance, effect size), behavioral analysis write-up, Related Work, reproducibility report | Sections 5–7 + README |

# 8. Project Timeline

| Phase | Weeks | Activities | Milestone |
| --- | --- | --- | --- |
| 1 — Foundation | 1–2 | CybORG++ environment setup + validation; codebase skeleton on GitHub; offline buffer collection (HQ + LQ); literature review finalization | Running env + both buffers ready |
| 2 — Baselines | 3–4 | PPO implementation + validation; AWR implementation; hyperparameter grid search for all algorithms; first 6 learning curves (PPO × 2 attackers, AWR × 2 buffers) | All baseline models running |
| 3 — Main Study | 5–7 | Full 5-seed × 500K step runs for all 6 factorial cells; PPO-WarmStart ablation; logging system captures all behavioral data in parallel | 34 runs complete, all data logged |
| 4 — Analysis | 8–9 | Statistical analysis (CIs, significance tests, effect sizes); action distribution plots; host compromise heatmaps; failure mode analysis; decision framework draft | All figures + insights complete |
| 5 — Writing | 10–18 | Full paper draft; internal review rounds; response to team feedback; final proofreading; submission to primary target venue | Paper submitted |
| 6 — Revision | 19–24 | Respond to reviewer comments; additional experiments if requested; resubmission if needed | Accepted / R&R addressed |

# 9. Risk Analysis & Mitigation

| Risk | Likelihood | Impact | Mitigation Strategy |
| --- | --- | --- | --- |
| AWAC does not outperform PPO in any condition | Medium | Medium | Frame as informative null result: “offline pre-training provides no significant benefit in this cyber context” — publishable empirical finding that saves others wasted effort |
| Attacker variation produces no measurable algorithm ranking difference | Low | High | Conduct sensitivity analysis on episode-level variance; if difference is <5%, argue it as evidence of algorithm robustness (positive result reframe) |
| CybORG++ version instability or breaking changes | Low | High | Pin to specific commit hash on Day 1; all team members use identical conda environment (environment.yml in repo) |
| M4 MPS backend causes non-determinism in seeds | Medium | Medium | Validate CPU vs MPS on 3 seeds before full runs; report if MPS is used and note any discrepancies |
| Behavioral analysis produces no clear qualitative differences | Low | Medium | Pre-register hypotheses before running (OSF.io); if no difference found, report as null — still a contribution |
| Rejection at primary venue | Medium | Low | Queue: IEEE Access → MDPI Electronics → Applied Sciences. All Q3/Q4, 2–6 month turnaround |

# 10. Computational Resources

All experiments are designed to run without cloud compute on Apple Silicon M4 using the MPS backend via PyTorch.

Compute Budget Estimate

Main factorial: 6 cells × 5 seeds × ~6 hrs = ~180 hrs Ablations: 4 cells × 5 seeds × ~6 hrs = ~120 hrs Total: ~300 hrs training time Parallelization: Run 4 seeds simultaneously (separate processes, M4 has sufficient RAM) Wall-clock: ~300 ÷ 4 = ~75 hrs ≈ 4–5 days of dedicated compute Logging: Weights & Biases (free tier) — real-time curves accessible by all team members Storage: ~2 GB total for checkpoints + logs (all 34 runs)

# 11. Target Publication Venues

| Venue | Tier | Scope Fit | Est. Turnaround | Priority |
| --- | --- | --- | --- | --- |
| IEEE Access | Q2–Q3 | Broad engineering; accepts empirical RL | 3–6 months | 1st choice |
| MDPI Electronics | Q3 | Applied AI/CS; empirical studies welcome | 2–4 months | 2nd choice |
| MDPI Applied Sciences | Q3 | Interdisciplinary AI + cybersecurity | 2–3 months | 3rd choice |
| J. Cybersecurity & Privacy (MDPI) | Q4 | Direct domain fit; fast turnaround | 2–3 months | Backup |
| Computers & Security (Elsevier) | Q1 (Stretch) | Top cybersecurity venue; if results are strong | 6–12 months | Ambitious target |

Strategy: Submit to IEEE Access first (broadest readership, fastest editorial response for a Q2 venue). Simultaneously prepare MDPI Electronics version as backup. Do not submit to Q1 venues until the team has mentor feedback on paper quality.

# 12. Key References

[1]  Schulman et al. (2017). Proximal Policy Optimization Algorithms. arXiv:1707.06347.

[2]  Peng et al. (2019). Advantage-Weighted Regression: Simple and Scalable Off-Policy RL. arXiv:1910.00177.

[3]  Nair et al. (2021). AWAC: Accelerating Online RL with Offline Datasets. arXiv:2006.09359.

[4]  Standen et al. (2021). CybORG: A Gym for the Development of Autonomous Cyber Agents. arXiv:2108.09118.

[5]  Baiocco et al. (2024). CybORG++: An Enhanced Gym for the Development of Autonomous Cyber Agents.

[6]  Singh et al. (2024). Hierarchical MARL for Cyber Network Defense. arXiv:2410.17351.

[7]  Morris et al. (2025). Combining SL and RL for a Generic Defensive Cyber Agent. MDPI J. Cybersecurity & Privacy.

[8]  Yue et al. (2023). Offline Prioritized Experience Replay. arXiv:2306.05412.

[9]  Palmer et al. (2023). Deep RL for Autonomous Cyber Defence: A Survey. arXiv:2310.07745.

[10] Levine et al. (2020). Offline Reinforcement Learning: Tutorial, Review, and Perspectives. arXiv:2005.01643.

Immediate Next Steps (Week 1)

Day 1: Fork CybORG++ repo; pin commit; create shared GitHub repo with conda environment.yml. Day 2: All 4 members validate CybORG++ runs end-to-end on their machines. Day 3: M2 begins HQ + LQ buffer collection; M1 begins PPO implementation. Day 5: First team sync — review RQ hypotheses together; pre-register on OSF.io. Week 2: M3 sets up W&B logging; M4 completes Related Work draft for team review.

This proposal is a living document. It will be updated after mentor onboarding to incorporate domain-specific feedback before final journal submission.